## SOP Build Status
Crystal People — SOP vs Build Status Tracker
SOP Document: HR-SOP-002 v1.0 ¦ As of: 26 March 2026
S.No | SOP Section | Feature / Requirement | Status | Phase | Remarks
SOP 3. Roles — User Roles & Permissions
1 | 3 | 4 roles: Employee, Manager, HR, MD/CEO | Done | 1 | JWT auth with role-based access
2 | 3 | Role-based visibility (Can See / Can Do per role table) | Done | 1 | Enforced in all API routes + sidebar
3 | 3 | Key control: Employee cannot self-approve goals/ratings | Done | 2C | Manager and employee always different
SOP 4. Employee Types — Two Employee Types
4 | 4.1 | White collar — scored against monthly goals | Done | 2C | Goals + 3 behaviours
5 | 4.1 | Min 3, max 5 goals at all times | Done | 2C | Validated in goal API
6 | 4.1 | Cannot drop below 3 without replacement | Done | 2C | Enforced in drop goal logic
7 | 4.1 | Dropped goals require mandatory written reason | Done | 2C | Drop_Reason field required
8 | 4.1 | New mid-month goals active immediately, scored next month | Done | 2C | Created_At tracked
9 | 4.2 | Blue collar — fixed task scorecard | Done | 2C | Tasks sheet + scoring
10 | 4.2 | 3–5 tasks per employee, fixed for year | Done | 2C | Manager sets via Team Tasks UI
11 | 4.2 | Each task scored 1–5 monthly by manager | Done | 2C | Monthly_Scores JSON in Tasks sheet
12 | 4.3 | 3 behavioural dimensions (Attendance, Teamwork, Ownership) | Done | 2C | BEHAVIOUR_DIMENSIONS constant
SOP 5. Rating Scale — The Rating Scale
13 | 5 | 1–5 scale with labels (Outstanding → Unsatisfactory) | Done | 2C | getRatingBand() in utils.ts
14 | 5 | Simple average of all dimensions, no weighting | Done | 2C | computeAverage() in utils.ts
SOP 6. Weekly Cycle — The Weekly Cycle — Every Friday
15 | 6.1 | Employee weekly reflection (4 fields + mood) | Done | 2B | Weekly_Reflections sheet
16 | 6.2 | Manager weekly check-in (5 fields with visibility rules) | Done | 2B | Weekly_Checkins sheet
17 | 6.2 | Concern field visible to HR/MD only, never to employee | Done | 2B | Filtered in API response
18 | 6.3 | Employee acknowledgement of check-in | Done | 2B | Acknowledged_At in reflections
19 | 6.3 | Saturday auto reminder to non-submitters | Not Built | 3 | Needs scheduled job
20 | 6.3 | Monday — pending visible to HR | Not Built | 3 | Needs escalation dashboard
21 | 6.3 | Missed reflections tracked, visible to MD | Not Built | 3 | Needs exec escalation view
SOP 7. Monthly Cycle — The Monthly Cycle
22 | 7 | Day 1 — Review window opens, employees & managers notified | Partial | 3 | Window logic exists, auto-notify not built
23 | 7 | Day 1–5 — Employee self-scores all dimensions | Done | 2C | Self-score page + API
24 | 7 | Day 1–10 — Manager scores each team member | Done | 2C | Score-team page + API
25 | 7 | After scoring — Manager writes review notes + next month focus | Done | 2D | Stored in Review_Cycles
26 | 7 | After manager submits — Employee acknowledges review | Done | 2D | Acknowledge API + My Review page
27 | 7 | Day 3 — First auto reminder to non-scorers | Not Built | 3 | Needs scheduled job
28 | 7 | Day 6 — Second auto reminder | Not Built | 3 | Needs scheduled job
29 | 7 | Day 7 — Pending reviews visible to HR | Partial | 2D | HR Monitor page shows all statuses
30 | 7 | Day 10 — Pending visible to MD, affects manager's own score | Not Built | 3 | Needs exec dashboard + penalty logic
31 | 7 | Day 11 — Window closes, scores locked for the month | Not Built | 3 | Manual lock exists, auto-lock not built
32 | 7.1 | Self-score: ≥2 point gap flagged for discussion | Done | 2D | Flagged_Dimensions in Review_Cycles
33 | 7.2 | AI validation of review notes (harsh/vague/unconstructive) | Done | 2D | ai-review.ts + validate-notes API
34 | 7.3 | Weekly context shown in monthly scoring screen | Done | 2D | weekly-context API + collapsible UI
SOP 8. Increments — Annual Increment Process
35 | 8 | 12-month average score calculation | Not Built | 5
36 | 8 | MD sets increment percentage bands before April 1 | Not Built | 5
37 | 8 | HR computes individual increments per band | Not Built | 5
38 | 8 | MD approves full increment sheet | Not Built | 5
39 | 8 | Increment letter generation | Not Built | 5
SOP 9. First Login — First Login Experience
40 | 9 | One-time welcome screen explaining Crystal People | Done | 1 | First_Login_Done flag + password change
SOP 10. Org Mgmt — Org Management
41 | 10 | Excel upload for bulk employee setup/changes | Not Built | 4
42 | 10 | Quick edit — HR searches and edits any employee field | Done | 2A | Employee edit page + PATCH API
43 | 10 | New joiner before 15th — current month cycle | Not Built | 6 | Edge case logic
44 | 10 | New joiner after 15th — starts next month | Not Built | 6 | Edge case logic
45 | 10 | Employee exit — marked inactive, history preserved | Partial | 2A | Status field exists, no dedicated exit flow
46 | 10 | Reporting change — effective next month | Not Built | 6 | Edge case logic
47 | 10 | Manager exits — team flagged unassigned | Not Built | 6 | Edge case logic
48 | 10 | All org changes auto-logged (what, who, when) | Done | 2A | Org_Changes sheet + API
SOP 11. Controls — Key Controls
49 | 11 | No employee may score themselves without manager scoring | Done | 2C | Status flow enforced
50 | 11 | No increment without MD written approval | Not Built | 5 | Increment feature pending
51 | 11 | All cycles must be completed + acknowledged before lock | Done | 2D | Lock requires manager_scored or acknowledged
52 | 11 | Manager penalty if team reviews not done by Day 10 | Not Built | 3 | Needs penalty logic
53 | 11 | Rating 1 employees = no increment (MD exception only) | Not Built | 5 | Increment feature pending
54 | 11 | Increment amounts strictly confidential between employees | Not Built | 5 | Increment feature pending
55 | 11 | Manager concern flags never visible to employee | Done | 2B | Filtered in API
SOP 12. Escalation — Escalation Matrix
56 | 12 | Employee disputes rating — HR mediates within 3 days | Not Built | 6
57 | 12 | Manager misses review deadline — HR escalates to dept head | Not Built | 3
58 | 12 | Employee misses reflection — auto reminder + HR visibility | Not Built | 3
59 | 12 | Goal/task change request — HR facilitates discussion | Not Built | 6
60 | 12 | Increment budget exceeded — HR presents to MD | Not Built | 5
61 | 12 | Employee refuses to acknowledge — HR documents, MD notified | Not Built | 6
SOP 13. Backend — Google Sheets Backend Structure
62 | 13 | Employees sheet | Done | 1 | 14 columns
63 | 13 | Managers sheet | Done | 1 | Manager-Employee lookup
64 | 13 | Review_Cycles sheet | Done | 2C | 15 columns incl. AI flags
65 | 13 | Goals sheet | Done | 2C | 13 columns
66 | 13 | Tasks sheet | Done | 2C | 9 columns
67 | 13 | Weekly_Reflections sheet | Done | 2B | 9 columns
68 | 13 | Weekly_Checkins sheet | Done | 2B | 10 columns
69 | 13 | Org_Changes sheet | Done | 2A | 7 columns
70 | 13 | Notifications sheet | Done | 2D | 7 columns
71 | 13 | Config sheet | Done | 1 | Key-Value pairs
72 | 13 | SEQUENCES sheet | Done | 1 | Auto-increment IDs
Summary
Done
Partial
Not Built
Total Items
Completion %
Phase-wise Breakdown
Phase | Description | Items | Done | Status
1 | Foundation & Auth
2A | Employee & Org Mgmt
2B | Weekly Cycle
2C | Monthly Scoring & Tasks
2D | Review Lifecycle & Notifications
3 | Automation & Escalation
4 | History, Feedback & Reports
5 | Annual Increments
6 | Executive & Edge Cases

## Completed
Crystal People — Completed Features
Total: 43 items
S.No | SOP Section | Feature / Requirement | Status | Phase | Remarks
1 | 3 | 4 roles: Employee, Manager, HR, MD/CEO | Done | 1 | JWT auth with role-based access
2 | 3 | Role-based visibility (Can See / Can Do per role table) | Done | 1 | Enforced in all API routes + sidebar
3 | 3 | Key control: Employee cannot self-approve goals/ratings | Done | 2C | Manager and employee always different
4 | 4.1 | White collar — scored against monthly goals | Done | 2C | Goals + 3 behaviours
5 | 4.1 | Min 3, max 5 goals at all times | Done | 2C | Validated in goal API
6 | 4.1 | Cannot drop below 3 without replacement | Done | 2C | Enforced in drop goal logic
7 | 4.1 | Dropped goals require mandatory written reason | Done | 2C | Drop_Reason field required
8 | 4.1 | New mid-month goals active immediately, scored next month | Done | 2C | Created_At tracked
9 | 4.2 | Blue collar — fixed task scorecard | Done | 2C | Tasks sheet + scoring
10 | 4.2 | 3–5 tasks per employee, fixed for year | Done | 2C | Manager sets via Team Tasks UI
11 | 4.2 | Each task scored 1–5 monthly by manager | Done | 2C | Monthly_Scores JSON in Tasks sheet
12 | 4.3 | 3 behavioural dimensions (Attendance, Teamwork, Ownership) | Done | 2C | BEHAVIOUR_DIMENSIONS constant
13 | 5 | 1–5 scale with labels (Outstanding → Unsatisfactory) | Done | 2C | getRatingBand() in utils.ts
14 | 5 | Simple average of all dimensions, no weighting | Done | 2C | computeAverage() in utils.ts
15 | 6.1 | Employee weekly reflection (4 fields + mood) | Done | 2B | Weekly_Reflections sheet
16 | 6.2 | Manager weekly check-in (5 fields with visibility rules) | Done | 2B | Weekly_Checkins sheet
17 | 6.2 | Concern field visible to HR/MD only, never to employee | Done | 2B | Filtered in API response
18 | 6.3 | Employee acknowledgement of check-in | Done | 2B | Acknowledged_At in reflections
23 | 7 | Day 1–5 — Employee self-scores all dimensions | Done | 2C | Self-score page + API
24 | 7 | Day 1–10 — Manager scores each team member | Done | 2C | Score-team page + API
25 | 7 | After scoring — Manager writes review notes + next month focus | Done | 2D | Stored in Review_Cycles
26 | 7 | After manager submits — Employee acknowledges review | Done | 2D | Acknowledge API + My Review page
32 | 7.1 | Self-score: ≥2 point gap flagged for discussion | Done | 2D | Flagged_Dimensions in Review_Cycles
33 | 7.2 | AI validation of review notes (harsh/vague/unconstructive) | Done | 2D | ai-review.ts + validate-notes API
34 | 7.3 | Weekly context shown in monthly scoring screen | Done | 2D | weekly-context API + collapsible UI
40 | 9 | One-time welcome screen explaining Crystal People | Done | 1 | First_Login_Done flag + password change
42 | 10 | Quick edit — HR searches and edits any employee field | Done | 2A | Employee edit page + PATCH API
48 | 10 | All org changes auto-logged (what, who, when) | Done | 2A | Org_Changes sheet + API
49 | 11 | No employee may score themselves without manager scoring | Done | 2C | Status flow enforced
51 | 11 | All cycles must be completed + acknowledged before lock | Done | 2D | Lock requires manager_scored or acknowledged
55 | 11 | Manager concern flags never visible to employee | Done | 2B | Filtered in API
62 | 13 | Employees sheet | Done | 1 | 14 columns
63 | 13 | Managers sheet | Done | 1 | Manager-Employee lookup
64 | 13 | Review_Cycles sheet | Done | 2C | 15 columns incl. AI flags
65 | 13 | Goals sheet | Done | 2C | 13 columns
66 | 13 | Tasks sheet | Done | 2C | 9 columns
67 | 13 | Weekly_Reflections sheet | Done | 2B | 9 columns
68 | 13 | Weekly_Checkins sheet | Done | 2B | 10 columns
69 | 13 | Org_Changes sheet | Done | 2A | 7 columns
70 | 13 | Notifications sheet | Done | 2D | 7 columns
71 | 13 | Config sheet | Done | 1 | Key-Value pairs
72 | 13 | SEQUENCES sheet | Done | 1 | Auto-increment IDs
Phase | Description | Items | Done | Status

## Pending
Crystal People — Pending / Not Built
Total: 30 items
S.No | SOP Section | Feature / Requirement | Status | Phase | Remarks
19 | 6.3 | Saturday auto reminder to non-submitters | Not Built | 3 | Needs scheduled job
20 | 6.3 | Monday — pending visible to HR | Not Built | 3 | Needs escalation dashboard
21 | 6.3 | Missed reflections tracked, visible to MD | Not Built | 3 | Needs exec escalation view
22 | 7 | Day 1 — Review window opens, employees & managers notified | Partial | 3 | Window logic exists, auto-notify not built
27 | 7 | Day 3 — First auto reminder to non-scorers | Not Built | 3 | Needs scheduled job
28 | 7 | Day 6 — Second auto reminder | Not Built | 3 | Needs scheduled job
29 | 7 | Day 7 — Pending reviews visible to HR | Partial | 2D | HR Monitor page shows all statuses
30 | 7 | Day 10 — Pending visible to MD, affects manager's own score | Not Built | 3 | Needs exec dashboard + penalty logic
31 | 7 | Day 11 — Window closes, scores locked for the month | Not Built | 3 | Manual lock exists, auto-lock not built
35 | 8 | 12-month average score calculation | Not Built | 5
36 | 8 | MD sets increment percentage bands before April 1 | Not Built | 5
37 | 8 | HR computes individual increments per band | Not Built | 5
38 | 8 | MD approves full increment sheet | Not Built | 5
39 | 8 | Increment letter generation | Not Built | 5
41 | 10 | Excel upload for bulk employee setup/changes | Not Built | 4
43 | 10 | New joiner before 15th — current month cycle | Not Built | 6 | Edge case logic
44 | 10 | New joiner after 15th — starts next month | Not Built | 6 | Edge case logic
45 | 10 | Employee exit — marked inactive, history preserved | Partial | 2A | Status field exists, no dedicated exit flow
46 | 10 | Reporting change — effective next month | Not Built | 6 | Edge case logic
47 | 10 | Manager exits — team flagged unassigned | Not Built | 6 | Edge case logic
50 | 11 | No increment without MD written approval | Not Built | 5 | Increment feature pending
52 | 11 | Manager penalty if team reviews not done by Day 10 | Not Built | 3 | Needs penalty logic
53 | 11 | Rating 1 employees = no increment (MD exception only) | Not Built | 5 | Increment feature pending
54 | 11 | Increment amounts strictly confidential between employees | Not Built | 5 | Increment feature pending
56 | 12 | Employee disputes rating — HR mediates within 3 days | Not Built | 6
57 | 12 | Manager misses review deadline — HR escalates to dept head | Not Built | 3
58 | 12 | Employee misses reflection — auto reminder + HR visibility | Not Built | 3
59 | 12 | Goal/task change request — HR facilitates discussion | Not Built | 6
60 | 12 | Increment budget exceeded — HR presents to MD | Not Built | 5
61 | 12 | Employee refuses to acknowledge — HR documents, MD notified | Not Built | 6

## Phase Roadmap
Crystal People — Phase-wise Development Roadmap
SOP: HR-SOP-002 v1.0 ¦ As of: 26 March 2026
Phase | Phase Name | Feature | Status | Go-Live Need | Notes
Phase 1 -- Foundation & Auth |  |  | Complete
|  | Next.js 15 + TypeScript + Tailwind CSS setup | Done | Yes
|  | Google Sheets API integration (read/write/update/batch/cache) | Done | Yes
|  | Sheet schema validation system | Done | Yes
|  | JWT email/password authentication | Done | Yes
|  | 4 roles: employee, manager, hr, md | Done | Yes
|  | First login password change flow | Done | Yes
|  | Forgot password with reset token | Done | Yes
Phase 2A -- Employee & Org Management |  |  | In Progress
|  | Employee list + search (HR/MD) | Done | Yes
|  | Employee profile view + edit | Done | Yes
|  | Manager assignment (Manager_ID) | Done | Yes
|  | Org Changes audit log | Done | Yes
|  | Employee exit flow (mark inactive) | Partial | Nice to have | Status field exists, no dedicated UI
|  | Config management (month, year, windows) | Done | Yes
Phase 2B -- Weekly Cycle |  |  | Complete
|  | Employee weekly reflection (4 fields + mood) | Done | Yes | SOP 6.1
|  | Manager weekly check-in (5 fields) | Done | Yes | SOP 6.2
|  | Concern field visible to HR/MD only | Done | Yes | SOP 6.2 + 11
|  | Reflection acknowledgement by manager | Done | Yes | SOP 6.3
|  | Dashboard with weekly status cards | Done | Yes
|  | Pending actions widget | Done | Yes
|  | Role-based sidebar navigation | Done | Yes
Phase 2C -- Monthly Scoring & Tasks |  |  | Complete
|  | Employee self-scoring (white-collar: goals + 3 behaviours) | Done | Yes | SOP 7.1
|  | Employee self-scoring (blue-collar: tasks + 3 behaviours) | Done | Yes | SOP 7.1
|  | Goal management (create, edit, drop with reason) | Done | Yes | SOP 4.1
|  | Min 3 / max 5 goals enforcement | Done | Yes | SOP 4.1
|  | Task management API (CRUD, activate/deactivate) | Done | Yes | SOP 4.2
|  | Score dimensions engine | Done | Yes
|  | computeAverage + getRatingBand | Done | Yes | SOP 5
|  | Window enforcement (isWindowOpen per role) | Done | Yes | SOP 7
|  | Manager scoring with review notes + focus | Done | Yes | SOP 7.2
|  | Locked Average + Flagged Dimensions | Done | Yes | SOP 7.1
|  | 2+ point gap flagged for discussion | Done | Yes | SOP 7.1
|  | Score My Team page | Done | Yes
|  | Team Tasks UI page | Done | Yes
|  | Team Goals page | Done | Yes
|  | Self-Score page | Done | Yes
|  | My Goals page | Done | Yes
|  | My Tasks page | Done | Yes
|  | Team Overview page | Done | Yes
Phase 2D -- Review Lifecycle & Notifications |  |  | In Progress
|  | Employee acknowledgement API | Done | Yes | SOP 7
|  | My Review page (scores, comments, acknowledge) | Done | Yes
|  | AI review notes validation | Done | Yes | SOP 7.2
|  | Weekly context in monthly scoring | Done | Yes | SOP 7.3
|  | HR Review Monitor page | Done | Yes
|  | Lock Cycle API (single + bulk) | Done | Yes | SOP 7
|  | Notifications foundation (APIs + bell) | Done | Yes | SOP 13
|  | Notification triggers (score, acknowledge, lock) | Done | Yes
|  | HR Notifications admin page | Not Built | Nice to have | HR uses Monitor page
Phase 3 -- Automation & Escalation |  |  | Not Started
|  | Day 1 auto notify window open | Not Built | Nice to have | HR messages manually
|  | Day 3 first auto reminder | Not Built | Nice to have | HR sends from Monitor
|  | Day 6 second auto reminder | Not Built | Nice to have
|  | Day 7 auto-flag pending to HR | Not Built | No | Monitor already shows all
|  | Day 10 pending visible to MD + manager penalty | Not Built | No | Manual for month 1
|  | Day 11 auto window close + auto lock | Not Built | Nice to have | HR bulk locks manually
|  | Saturday auto reminder for missed reflections | Not Built | Nice to have | HR sends manually
|  | Monday missed reflections visible to HR | Not Built | No | Check sheet directly
|  | Missed reflections visible to MD | Not Built | No
|  | Manager deadline escalation | Not Built | No
|  | Full escalation dashboard | Not Built | No
Phase 4 -- History, Feedback & Reports |  |  | Not Started
|  | My History page (12-month trend) | Not Built | Nice to have | Only 1 month at launch
|  | My Feedback page (past manager feedback) | Not Built | Nice to have | My Review covers current
|  | HR Reports (dept-wise, score distribution) | Not Built | Nice to have | Export from Google Sheets
|  | Excel bulk upload for employees | Not Built | Nice to have | Manual entry or sheet edit
Phase 5 -- Annual Increments |  |  | Not Started
|  | 12-month average score calculation | Not Built | No | Not needed until March 2027
|  | MD sets increment percentage bands | Not Built | No
|  | HR computes individual increments | Not Built | No
|  | MD approves increment sheet | Not Built | No
|  | Increment letter generation | Not Built | No
Phase 6 -- Executive & Edge Cases |  |  | Not Started
|  | Executive Dashboard (org-wide for MD) | Not Built | No | MD uses HR Admin pages
|  | Rating Overrides by MD | Not Built | No | Edit sheet directly
|  | Approve Increments page | Not Built | No | Phase 5 dependency
|  | Employee disputes rating flow | Not Built | No | Manual process
|  | Goal/task change request flow | Not Built | No | Manual process
|  | Employee refuses to acknowledge | Not Built | No | Manual process
|  | Org edge cases (joiner cutoff, mgr exit) | Not Built | No | Manual handling
Go-Live Need Legend
Yes | Must have for go-live -- already built and working
Nice to have | Useful but HR can work around it manually for month 1
No | Not needed for April 1 launch -- can be built later